## Sheet1
PROJECT NAME		PROJECT DURATION		PROJECT START DATE		PROJECT ENDING

Lofthus frukt og saft		3 weeks		11/19/18		12/03/18

Task ID		Task Description		Task Duration		Start Date		End Date	11/19/18	11/20/18	11/21/18	11/22/18	11/23/18	11/24/18	11/25/18	11/26/18	11/27/18	11/28/18	11/29/18	11/30/18	12/01/18	12/02/18	12/03/18
Task 1	Making examples for different websites			1 Day		11/19/18		11/20/18
Task 2	Meet with client / gather information			2 Days		11/20/18		11/22/18
Task 3	Hire workers			3 Days		11/21/18		11/24/18
Task 4	Making HTML for website			1 Day		11/22/18		11/23/18
Task 5	Make CSS for website			2 Days		11/24/18		11/26/18
Task 6	Photograph are/object for website/promo			1 Day		11/24/18		11/25/18
Task 7	Insert photo's into web page			1 Day		11/25/18		11/26/18
Task 8	Start promote for the website/company			2 Days		11/26/18		11/28/18
Task 9	Second meeting with company			1 Day		11/26/18		11/27/18
Task 10	Check up on copy writing			1 Day		11/27/18		11/28/18
Task 11	Set up servers for website			2 Days		11/29/18		12/01/18
Task 12	Deliver finish product			0 Days		12/03/18		12/03/18